## Sheet1
Project Budget Template
Project Name: | Personal shopper
Company : | Hyper panda
Project Manager:
Materials
|  |  | Planned day | $/day | UNITS | $/UNITS | Travel | Equipment | BUDGETED
WBS | Project Tasks | Assigned To:
1 | Initiating | manager | 16 | 2992 |  |  |  |  | 2992
1.1 | Develop business case | developer | 4 | 1632 |  |  |  |  | 1632
1.2 | perform feasibility study | manager | 5 | 935 |  |  |  |  | 935
1.3 | establish terms of reference | developer | 4 | 1632 |  |  |  |  | 1632
1.4 | appoint project team | manager | 3 | 561 |  |  |  |  | 561
1.5 | set-up project office | analyst | 3 | 741 |  |  |  |  | 741
1.6 | perform stage-gate | manager | 1 | 187 |  |  |  |  | 187
2 | Planning | manager | 9 | 1683 |  |  |  |  | 1683
2.1 | planning initiation | manager | 3 | 561 |  |  |  |  | 561
2.2 | resource planning | engineer | 3 | 2451 |  |  |  |  | 2451
2.3 | quality planning | engineer | 1 | 187 |  |  |  |  | 187
2.4 | define the goals | manager | 1 | 187 |  |  |  |  | 187
2.5 | phase review | developer | 1 | 408 |  |  |  |  | 408
3 | Analysis | analyst | 20 | 4940 |  |  |  |  | 4940
3.1 | Gathering business requirements | analyst | 1 | 247 |  |  |  |  | 247
3.2 | building trust with users | manager | 8 | 1496 |  |  |  |  | 1496
3.2 | documenting the system | developer | 2 | 816 |  |  |  |  | 816
3.3 | develop preliminary data and process models | developer | 2 | 816 |  |  |  |  | 816
4 | 4. Design | designer | 16 | 3584 |  |  |  |  | 3584
4.1 | implementation | programmer | 4 | 2926 |  |  |  |  | 2926
4.2 | system construction | programmer | 5 | 3720 |  |  |  |  | 3720
4.3 | installation/introducing | engineer | 2 | 1634 |  |  |  |  | 1634
4.4 | the system to the company | engineer | 5 | 4085 |  |  |  |  | 4085
4.5 | support plan for the system | developer | 1 | 408 |  |  |  |  | 408
5 | Develepment | developer | 22 | 8976 |  |  |  |  | 8976
5.1 | System maintenance | engineer | 1 | 817 |  |  |  |  | 817
5.2 | Develop System Modules | developer | 11 | 4488 |  |  |  |  | 4488
5.3 | Integrate System Modules | programmer | 7 | 5208 |  |  |  |  | 5208
5.4 | Perform Initial Testing | testing team | 3 | 63 |  |  |  |  | 63
5.5 | Development Complete | developer | 1 | 408 |  |  |  |  | 408
6 | Testing | testing team | 17 | 357 |  |  |  |  | 357
6.1 | Deploy Test Environment | testing team | 1 | 21 |  |  |  |  | 21
6.2 | Perform System Testing | testing team | 8 | 168 |  |  |  |  | 168
6.3 | Document Issues Found | testing team | 6 | 126 |  |  |  |  | 126
6.4 | completion of testing | testing team | 1 | 21 |  |  |  |  | 21
6.5 | Correct Issues Found | testing team | 3 | 63 |  |  |  |  | 63
6.6 | Testing Complete | testing team | 1 | 21 |  |  |  |  | 21
7 | Training | HR | 11 | 1804 |  |  |  |  | 1804
7.1 | Train employees | HR | 3 | 492 |  |  |  |  | 492
7.2 | Customer guide | customer service team | 3 | 498 |  |  |  |  | 498
7.3 | Training Complete | HR | 1 | 164 |  |  |  |  | 164
8 | Documentation | HR | 8 | 1312 |  |  |  |  | 1312
8.1 | Technical Documentation | HR | 3 | 492 |  |  |  |  | 492
8.2 | User Documentation | HR | 5 | 820 |  |  |  |  | 820
8.3 | Project Complete | HR | 1 | 164 |  |  |  |  | 164
9 | Closure | manager | 1 | 187 |  |  |  |  | 187
9.1 | perform project closure | manager | 1 | 187 |  |  |  |  | 187
9.2 | review completion | manager | 1 | 187 |  |  |  |  | 187
| SUBTOTAL | [7 empty] | 65873